## Read me
Production Lines 1-12 - Issue & Request Tracker
Save this file to SharePoint or a Teams channel and everyone can edit it at once in the browser.
How to use it
1. Raise a ticket on the Tickets sheet - one row per issue or request. Fill the white cells; the grey ones calculate themselves.
2. Pick from the dropdowns for Ticket Type, Line, Category, Severity, Status and Shift so the counts on the Dashboard stay accurate.
3. Update Status as work progresses. Set Date Closed when it is finished - that is what drives "closed this week".
4. The Dashboard sheet recalculates on its own. Nothing to press.
Which cells you edit
White background = you type here.
Grey background = formula, leave it alone (Ticket ID and Age (days) on Tickets, everything on the Dashboard).
Row 2 of the Tickets sheet is an example. Delete it before you start.
Severity - what the levels mean
S1 - Line Down the line is stopped. Raise it here AND call the shift lead; do not wait for the ticket.
S2 - Major running but degraded, quality or rate at risk. Same shift.
S3 - Minor line running normally. Plan it into maintenance.
S4 - Cosmetic improvement or backlog. Review at the weekly meeting.
Changing the setup
Rename a line, change its owner or its state -> Lines sheet
Add a category, status or severity -> Choices sheet
More than 200 tickets -> copy the last row of the Tickets sheet downwards; the formulas and dropdowns come with it
Worth knowing
Everyone who can open this file can edit any row, including other people's. A SharePoint list can restrict that per person; a spreadsheet cannot.
There are no automatic notifications. If you want an alert when an S1 is raised, that needs the SharePoint list version plus a Power Automate flow.
Attachments: paste a photo straight into the Details cell, or keep photos in a folder beside this file.

## Dashboard
Production Lines 1-12
Every figure here is a formula over the Tickets sheet. Nothing to refresh.
OPEN TICKETS |  | LINES DOWN (S1) |  | OLDEST OPEN (DAYS) |  | CLOSED LAST 7 DAYS
New, triaged, in progress, waiting |  | Stopped right now |  | Longest-running open ticket |  | By Date Closed
Open tickets by line | [6 empty] | By status
Line | Name | Open | S1 | S2 | S3 | S4 | Status | Tickets
New
Triaged
In Progress
Waiting on Parts
Resolved
Closed
Open by category
[7 empty] | Category | Open
Mechanical
Electrical
Controls / PLC
Quality defect
Safety
Material supply
Utilities
Changeover
Housekeeping
Other
Counts cover rows 2-200 of the Tickets sheet. If you extend past row 200, widen the ranges in these formulas to match.

## Tickets
Ticket ID | Date Raised | Ticket Type | Line | Category | Severity | Status | Summary | Details | Reported By | Shift | Downtime (min) | Assigned To | Target Date | Date Closed | Resolution | Age (days)
|  | Issue | L03 | Electrical | S1 - Line Down | In Progress | Drive motor tripping under load | Overload trips within ten minutes of a full-rate start. Line stopped. | J. Okafor | B - Afters | 95
Formulas:
Age (days) = IF(OR([Line]="",[Date Raised]=""),"",IF(OR([Status]="Resolved",[Status]="Closed"),"",TODAY()-[Date Raised]))
Note on A1: Calculated - do not type here. Numbering starts at 1001.
Note on Q1: Calculated - days since Date Raised. Goes blank once the ticket is Resolved or Closed.

## Lines
Production lines
Rename a line here and every dropdown and count follows. Line Code is what tickets store - keep the padding (L01, not L1) so it sorts correctly.
Line Code | Line Name | Line Owner | Line State | Open tickets
L01 | Line 1 |  | Running
L02 | Line 2 |  | Running
L03 | Line 3 |  | Running
L04 | Line 4 |  | Running
L05 | Line 5 |  | Running
L06 | Line 6 |  | Running
L07 | Line 7 |  | Running
L08 | Line 8 |  | Running
L09 | Line 9 |  | Running
L10 | Line 10 |  | Running
L11 | Line 11 |  | Running
L12 | Line 12 |  | Running

## Choices
Ticket Type | Category | Severity | Status | Shift | Line State | Edit these lists to change what the dropdowns offer.
Issue | Mechanical | S1 - Line Down | New | A - Days | Running | Add a value directly under the last one in a column and the dropdown on the Tickets sheet picks it up. Renaming a value does NOT update tickets already using the old wording, and the colour rules on the Tickets sheet match the Severity and Status wording exactly - change those under Home > Conditional Formatting if you reword them.
Request | Electrical | S2 - Major | Triaged | B - Afters | Degraded
| Controls / PLC | S3 - Minor | In Progress | C - Nights | Down
| Quality defect | S4 - Cosmetic | Waiting on Parts |  | Planned Downtime
| Safety |  | Resolved
| Material supply |  | Closed
Utilities
Changeover
Housekeeping
Other